## PERT & CPM Model
PROJECT MANAGEMENT: PERT & CPM INTERACTIVE MODEL
Data Engineering & Application Deployment Project
💡 Note: You can modify the Optimistic (a), Most Likely (m), and Pessimistic (b) estimates below. All PERT parameters, ES/EF/LS/LF, float, critical path flags, and project completion metrics update automatically!
Activity Code | Activity Description | Predecessors | Optimistic (a) | Most Likely (m) | Pessimistic (b) | Expected Duration (TE) | Variance (σ²) | Early Start (ES) | Early Finish (EF) | Late Start (LS) | Late Finish (LF) | Total Slack / Float | Is Critical Path?
A | Collect existing data | None | 1 | 2 | 3 |  |  | 0
B | Design Database / Data Structure | A | 2 | 3 | 6
C | Digitize inventory / get insights | B | 2 | 4 | 6
D | Digitize transactions / get insights | B | 3 | 5 | 7
E | Build New Application for new data | B | 4 | 7 | 10
F | Deploy new app | E | 1 | 2 | 3
G | Exploratory Data Analysis (EDA) | C, D, F | 3 | 4 | 8
H | Business Analysis | G | 2 | 3 | 4
PERT & CPM PROJECT SUMMARY DASHBOARD
Project Expected Duration (TE) |  |  |  | Project Variance (σ²) |  |  |  | Project Std Deviation (σ)
Interactive Completion Probability Calculator
Target Completion Deadline (Days) |  | Z-Score |  | Completion Probability
24
Network Paths Analysis
Path ID |  | Path Description / Sequence |  |  |  | Path Duration Formula |  |  | Path Length (Days) |  | Critical Path Status
Path 1 (Inventory Track) |  | A -> B -> C -> G -> H |  |  |  | Formula based on TE
Path 2 (Transactions Track) |  | A -> B -> D -> G -> H |  |  |  | Formula based on TE
Path 3 (New App Track) |  | A -> B -> E -> F -> G -> H |  |  |  | Formula based on TE